## Pianificazione progetto
Planning - 4/October to 4/November
[6 empty] | 1 |  |  | Duration of the plan | [6 empty] | Actual start | [5 empty] | % progress | [6 empty] | Extra time than actual duration | [7 empty] | % progress (extra time)
ACTIVITY | START | DURATION OF THE PLAN | START - ACTUAL | DURATION OF THE PLAN - ACTUAL | % COMPLETION | PERIOD | [30 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | November
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Configure debugger - qt configured | 4 | 5 | 4 | 3 | 75%
Write global planner for the zig-zag trajectory | 9 | 7 | 9 | 7 | 90%
Make a bag file and read the path - make Matlab script and compare the trajectory, see results | 16 | 4 | 16 | 4 | 10%
Configure Global & Local Planner param | 20 | 7 | 20 | 7 | 0%
Find the coordinates of the Husky and set Amcl to zero | 27 | 7 | 27 | 8 | 0%
Understand Amcl.cpp code | 34 | 7 | 34 | 7 | 0%
Write the measurement model of the Amcl | 41 | 14 | 41 | 14 | 0%
Fire the Wireless Plugin | to be defined
Setup documentation for Qtcreator
Notes on the activities